## Slide 1
Project Status Report
Project Phase: Execution
Reporting period: 19/09/2024 to 16/111/2024
Overall Status: Yellow
Project Owner (PO): Department of Information Systems
Business Manager (BM): Professor João Varajão
Project Manager (PM): Catarina Pereira
Project Team (PT)/Solution Provider (SP): Catarina Pereira, Inês Neves, Leonardo Martins and Rodrigo Castillo
Project Status Summary
To date, the project has completed 65% of its tasks.
Project Indicator (at current state)
Status: Yellow
Baseline delivery date: 16th November, 2024
Forecasted delivery date: 16th November, 2024
Academic year: 2024/2025
Issues
Status: Green
This project has no open situations.
Milestones
19/09/2024 - Project Initialization
12/10/2024 - Delivery of Project Charter and Poster
02/11/2024 - Delivery of the 1st version of the Project Plan
16/11/2024 - Delivery of Status/ Control Reports
21/11/2024 - Mock Up Delivery
End Nov - Employee Training
End Nov - Quality Certificate
10/12/2024 - Final Delivery
12/12/2024 - Project Presentation
12/12/2024 - Individual Meeting
Gestão de Projetos de Tecnologias e Informática (GPTI)
Engenharia de Telecomunicações e Informática
Departamento de Sistemas de Informação - Escola de Engenharia
Legend
Completed as planned
Open or under development as planned
Deliverables
Application Mockup
User Manual
Application Maintenance Manual
Fully functional mobile application
Source Code of the Application
Project Changes
Status: Green
Category Application - Development of just one interactive game.
Project Work State
Project Cost State
Top Risks
Status: Yellow
Loss of team member: O: 1│I: 5│S:5
Loss of client’s trust: O: 2│I: 5│S:10
Exceeding the stipulated budget: O: 5│I: 3│S:15
Delay in delivering milestones/ deliverables: O: 5│I: 2│S:10
Planned Cost (BCWS): 3744,78 Actual Cost (ACWP): 3893,53 Earned Value (BCWP): 3905,04 | Accounting Variance: -148,75 SPI: 1,04 CPI: 1,00
Legend
O: Occurrence I: Impact S: Seriousness | Active Risk Possible Risk