## Folha1
Description | Details | Justification | Estimation Price
Team Salary | 4 people 10€/hour; 14 weeks; 6 hours/week. | The team consists of 4 members, each working 6 hours weekly for 14 weeks. Total: 336 hours at 10€/hour. | 3360
Traveling | 169.2 km/day; 34,18€ on tolls and fuel; 1 day a week. | Travel once a week for 14 weeks. The cost is 34.12€/day for fuel and tolls, totaling 168€. | 478.52
Equipment | 4 computers. | To calculate the value of a 4-year-old computer for a 14-week project, the straight-line depreciation method is used, spreading the cost over its 4-5 year lifespan. The remaining value is then depreciated for the 14-week project. Estimated useful life: 4 years Annual depreciation: 1000€/4=250€ After 3 years, the depreciated value will be:1000€-(3✕250€)=250€ The weekly price is: 250€/52=4,81€/per week For 14 weeks: 4,81€×14=67,31€ | 269.2308
Meeting Room | Rent for a conference room with projector and internet for 14 weeks. | Necessary for team meetings and presentations with stakeholders. | 600
Quality Certificate | Safety and performance audits. | To ensure compliance with technical requirements at the end of the project. | 160
Marketing costs | Promotional materials | Leaflets, posters and digital marketing | 800
Total |  |  | 5667.7508
140
1020
2360
1360
3400
680
3060
200
2000
275
375
450
400
250
200
1078

## PERT
Description | Optimistic Cost | Probable cost | Pessimistic cost | PERT | Reservation
Human Resources | 2240 | 3510 | 5120 | 3566.6667 | 56.6667 |  | 3510
Traveling | 402.64 | 478.52 | 532.56 | 474.88 | 3.64 |  | 410.16
Equipment | 201.9231 | 269.2308 | 336.5385 | 269.2308 | 0 |  | 230.7692
Room | 140 | 600 | 3400 | 990 | 390 |  | 514.2857
Quality Certificate | 100 | 120 | 500 | 180 | 60 |  | 120
Marketing Costs | 150 | 800 | 1500 | 808.3333 | 8.3333 |  | 400
Total | 3234.5631 | 5777.7508 | 11389.0985 | 6289.1108 | 518.64 | 6296.3908 | 5185.2149
To describe the reserves, the team used Programme Evaluation and Review Technique (PERT) estimation. The PERT estimate uses three estimates to calculate the probable duration of a task: the optimistic estimate (O), the most probable estimate (M) and the pessimistic estimate (P). The formula for PERT estimation is: Estimated Duration (ED)=(O+4M+P)/6
5877.7508

## Time Frame
Week | Human Resources | Equipment | Meeting Room | Quality Certificate | Marketing Costs | Reserves Costs | Total
1 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
2 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
3 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
4 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
5 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
6 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
7 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
8 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
9 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
10 | 274.18 | 19.2308 | 42.8571 | 500 |  | 38.7124 | 874.9803
11 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
12 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
13 | 274.18 | 19.2308 | 42.8571 |  |  | 38.7124 | 374.9803
14 | 274.18 | 19.2308 | 42.8571 |  | 800 | 38.7124 | 1174.9803
Total | 3838.52 | 269.2308 | 600 | 500 | 800 | 541.973 | 6549.7238